HOPE Platform Delivery Cycles & Task Ownership Sheet

Prepared from the roadmap report, current-vs-future flow analysis, end-to-end architecture/UI specification, shared mockup gallery, and the current Flutter codebase review.

| Field | Value |
| --- | --- |
| Prepared on | August 29, 2026 |
| Planning horizon | 25 working days across 3 execution cycles |
| Execution split | Cycle 1: UI & Refactor (10 days) ¦ Cycle 2: Integration (10 days) ¦ Cycle 3: Testing & Stabilization (5 days) |
| Important note | The requested percentage split totals 80%. This document keeps your exact 25-day division and reserves the remaining 20% as contingency for product-decision closure, UAT feedback, and spillover. |

Planning Basis

This delivery sheet is built around one key distinction that appears across the source pack: the roadmap and flow-analysis documents describe a future target platform that is broader than the current implementation, while the current Flutter project already contains partial patient, practitioner, dashboard, questionnaire, assessment-result, and session-review flows. The cycle plan therefore uses the current codebase as the build baseline and the attached UI/UX material as the target experience.

| Area | Observed Baseline | Target from Sources | Planned Cycle |
| --- | --- | --- | --- |
| Shared entry flow | Current app has welcome + role selection; no real auth flow | Splash, 3-slide onboarding, login, register, token check, role routing | C1+C2 |
| Patient baseline | Current app has session/questionnaire/results flow; assessment UX is partial and code/docs are not fully aligned | First-time medical history + baseline tests before plan activation | C1+C2 |
| Patient dashboard | Current dashboard exists but does not match the richer mockup target | Daily plan card, streaks, doctor note, history and profile polish | C1 |
| Session execution | Current build is single-path and glove-centric | Mode selection, glove path, camera path, guided video path, game path | C1+C2 |
| Smart glove layer | Current API/session flow exists but device connection UX is simplified | Real connection status, calibration/battery handling, disconnect behavior | C2 |
| Camera path | Not clearly implemented; documents treat measurement scope as open | Calibration flow with explicit product-decision guardrail | C2 |
| Doctor experience | Session list/detail review exists, but future dashboard and patient directory are broader | Dashboard, patient directory, patient profile detail, plan review actions | C1+C2 |
| ML + adaptive loop | Not implemented today | Recommendation review and future plan updates with doctor in the loop | Decision buffer / later phase |
| Testing coverage | Current test suite is minimal | Structured unit, widget, flow, device, and regression coverage | C3 |

Cycle Summary

| Cycle | Focus | Duration | Goal | Owner |
| --- | --- | --- | --- | --- |
| 1 | UI & Refactor | 10 days | Align the Flutter app structure and screens with the approved HOPE mockup system while cleaning reusable UI foundations. | ________ |
| 2 | Integration | 10 days | Connect the approved flows to backend, session state, device handling, and doctor/patient data transitions. | ________ |
| 3 | Testing & Stabilization | 5 days | Verify the full patient and doctor experience, harden failure paths, and ship a stable release candidate. | ________ |

Cycle 1 - UI & Refactor (10 Days)

Objective: bring the live Flutter UI closer to the approved mockup gallery, unify shared components, and clean structural issues before integration expands the surface area.

| ID | Task | Expected Output | Days | Dependency / Note | Owner |
| --- | --- | --- | --- | --- | --- |
| C1-01 | Design system cleanup | Unify colors, typography, buttons, cards, forms, chips, nav bars, and reusable spacing tokens across patient and doctor areas. | 1.5 | Needed before broad screen polish | ________ |
| C1-02 | Splash + onboarding UI | Implement or refine splash and 3-slide onboarding flow to match the mockup hierarchy, imagery, CTA flow, and persistence behavior. | 1.0 | Uses onboarding completion flag | ________ |
| C1-03 | Auth screen refactor | Refactor login/register/forgot-password presentation shells to match the target mockups and shared form behavior. | 1.5 | UI-only first; API comes in C2 | ________ |
| C1-04 | Role routing and shell cleanup | Clean the transition between splash, onboarding, auth, patient shell, and doctor shell so navigation structure is predictable. | 1.0 | Must not over-couple to future auth decisions | ________ |
| C1-05 | First-time assessment UX | Align the assessment/questionnaire stepper, chips, sliders, and guided test surfaces with the target baseline-assessment flow. | 1.5 | Keep current measurement logic separable | ________ |
| C1-06 | Patient dashboard + history UI | Refactor patient home, activity history, and session-details visuals to match the approved information hierarchy. | 1.5 | Build from existing screens instead of replacing blindly | ________ |
| C1-07 | Doctor dashboard + directory UI | Refactor doctor dashboard, patient directory/listing, session review, and settings/profile screens to the target layout. | 1.5 | Reuse cards/charts from shared UI pass | ________ |
| C1-08 | Assets, copy, and responsive polish | Clean duplicate mock assets, align labels, review localization strings, and fix overflow/spacing issues across supported screens. | 0.5 | Close visual debt before integration | ________ |

Cycle 2 - Integration (10 Days)

Objective: connect the refined UI to the real application flow, backend contracts, device lifecycle, and role-based data handling.

| ID | Task | Expected Output | Days | Dependency / Note | Owner |
| --- | --- | --- | --- | --- | --- |
| C2-01 | Authentication integration | Wire login/register/token persistence, logout, and role claims into the live app shell with secure storage and startup checks. | 1.0 | Depends on auth API readiness | ________ |
| C2-02 | User and relationship model | Define patient/doctor profile payload handling, role routing, and any patient-doctor linking required for dashboard data. | 0.5 | Needs backend contract clarity | ________ |
| C2-03 | Baseline assessment submit + gating | Persist first-time assessment results, mark completion state, and route patients correctly after first login. | 1.5 | Must preserve existing session logic where possible | ________ |
| C2-04 | Active plan + daily session start | Connect dashboard plan cards, session start actions, and daily-session context to backend/session state. | 1.0 | Bridges mockup target to current provider flow | ________ |
| C2-05 | Smart glove connection flow | Integrate discovery/connection status, readiness checks, calibration/battery indicators, and disconnect handling into the session flow. | 1.5 | Firmware/BLE protocol details must be explicit | ________ |
| C2-06 | Camera path implementation gate | Implement the selected camera pathway scope or build a guarded placeholder if measurement rules are still undecided. | 1.0 | Open product decision from source docs | ________ |
| C2-07 | Guided exercise runtime | Connect standard exercise screen(s) to live metrics, rep counting, progress, pause/resume, and measurement feedback. | 1.5 | Must support glove path first | ________ |
| C2-08 | Results + survey payload | Send post-session metrics, questionnaire/survey answers, and any feedback event to the backend in one coherent flow. | 1.0 | Needed before doctor review updates | ________ |
| C2-09 | Doctor dashboard data wiring | Connect patient list, patient detail, session detail, and plan-review surfaces to live API data and refresh rules. | 1.5 | Reuses current practitioner flows where valid | ________ |
| C2-10 | State/error/offline hardening | Normalize loading, retry, disconnect, empty, unauthorized, and no-internet handling across major flows. | 0.5 | Must be finished before C3 | ________ |

Cycle 3 - Testing & Stabilization (5 Days)

Objective: convert the integrated build into a stable release candidate through code-level tests, end-to-end verification, and rapid regression fixing.

| ID | Task | Expected Output | Days | Dependency / Note | Owner |
| --- | --- | --- | --- | --- | --- |
| C3-01 | Unit test coverage | Add tests for models, providers/cubits, API/service layers, and critical data mapping logic. | 1.0 | Prioritize session and auth logic | ________ |
| C3-02 | Widget/UI flow tests | Add widget tests for shared auth, onboarding, dashboard, assessment, and session-summary surfaces. | 1.0 | Focus on highest-risk user paths | ________ |
| C3-03 | End-to-end execution matrix | Run structured patient and doctor flow validation from app entry to session review, including role routing and survey completion. | 1.5 | Manual + automated where feasible | ________ |
| C3-04 | Failure-path QA | Verify disconnects, timeouts, no-internet behavior, missing data, permission denial, and retry scenarios. | 0.75 | Critical for glove/camera/session reliability | ________ |
| C3-05 | Regression fixes + release checklist | Resolve surfaced bugs, rerun core scenarios, and prepare a release-candidate checklist for handoff. | 0.75 | Final gate before signoff | ________ |

Reserved Buffer / Open Product Decisions

The source pack repeatedly identifies unresolved decisions that can affect estimate accuracy. The remaining 20% should stay intentionally uncommitted until these items are explicitly closed.

| Open Item | Why it matters | Suggested Handling |
| --- | --- | --- |
| Camera-based measurement scope | The documents do not settle whether the camera path is recording-only, CV-measured, or clinically scored. | Lock product scope before deep implementation; otherwise ship a guarded placeholder or assisted-capture mode. |
| Exact auth and account model | The roadmap requires multi-user auth, but the mechanism and role-assignment model are not fixed in the source pack. | Confirm identity provider, token format, roles, and patient-doctor linking early in C2. |
| Smart glove connection protocol | The future UX assumes richer device discovery/status than the current simplified app flow. | Document BLE/Wi-Fi pairing, battery, calibration, reconnect, and timeout rules before device integration closes. |
| ML recommendation authority | The docs are clear that ML recommends and the doctor approves, but the exact payload and approval UX are not specified. | Keep ML surfaces informational unless the backend and approval actions are fully defined. |
| HOPE Planet production scope | The game is a delivery layer, not a replacement for therapy, but gameplay scope and session rules are still broad. | Treat game integration as a controlled feature track, not as part of the base therapy validation path. |

Recommended Ownership Use

Use the Owner column to assign one directly responsible person per task. If a task has multiple contributors, place the lead owner in the table and track supporting contributors in your execution tool or sprint notes. Any task blocked by the open decisions above should be marked as conditional rather than silently estimated as straightforward engineering work.

Source Basis Reviewed

| Source | How it was used |
| --- | --- |
| HOPE_Platform_Roadmap_Report | Used to separate current implemented behavior from future roadmap scope and to capture the official phased roadmap plus open decisions. |
| HOPE_Current_vs_Future_Flow_Analysis | Used to define dependency-aware sequencing, the closed-loop model, and the AI-in-the-loop guardrail. |
| End-to-End System Architecture & UI/UX Specification | Used to map the target screen set, user flows, and integration points for patient and doctor journeys. |
| Mockup gallery images + referenced site | Used to refine the UI/refactor scope, screen grouping, and expected visual hierarchy. |
| Current Flutter codebase review | Used to anchor the plan to the real implementation baseline rather than planning only from future-state documents. |